## WBS 2
Reference WBS | Reviews During 2016 | Scheduled Date (as 5-12-16) | Done or Predicated
TPC Construction
40SBN/2.3.2.11 | TPC Preliminary Design Review | 2015-08-20 | Sept. 30,2015
40SBN/2.3.2.11 | TPC Design Review: APA Frame | 2016-02-08 08:00 | Feb. 23,2016
40SBN/2.3.2.10 | CPA Final Design Review (UK - Labor) (SBN-ND-TPCC)(FD) | 2016-05-17 08:00 | 2016-06-06
40SBN/2.3.2.11 | HV Feed Through Final Design Review (UK - Labor) (SBN-ND-TPCC)(FD) | 2016-05-17 08:00 | 2016-06-06
40SBN/2.3.2.12 | Field Cage Final Design Review (UK - Labor) (SBN-ND-TPCC)(FD) | 2016-06-01 08:00 | Oct 25,2016
40SBN/2.3.2.14 | TPC Wire Winding Final Design Review (UK - Labor) (SBN-ND-TPCC)(FD) | 2016-07-01 08:00 | Jan 18,2017 | July 27 to have wire-winding workshop, then to have design review in August-Sept
40SBN/2.3.5.7 | UK APA Wire Winding Readiness Review | 2016-09-23 17:00
40SBN/2.3.5.13 | UK APA Production QA/QC Review | 2017-05-15 17:00
40SBN/2.3.6.8 | US APA Wire Winding Readiness Review | 2016-12-28 17:00
40SBN/2.3.6.13 | US APA Production QA/QC Review | 2017-07-21 17:00
40SBN/2.3.7.6 | CPA Production QA/QC and Installation Review | 2017-03-31 17:00
40SBN/2.3.8.7 | HV and Feed Through Production and Installation Review | 2017-05-17 17:00
40SBN/2.3.9.6 | Field Cage Production QA/QC and Installation Review | 2017-02-23 17:00
40SBN/2.3.10.4 | Field Cage Production and Installation Review | 2017-05-16 17:00
40SBN/2.3.10.6 | TPC Connection Frames Installation Review | 2017-07-31 17:00
40SBN/2.3.11.7 | TPC Assembly Tooling Installation Review | 2017-06-26 17:00
PMT Light Detector
40SBN/2.4.1.11 | PMT Integration and Installation Design Review | 2016-07-21 08:00 | Nov 18,2016
40SBN/2.4.2.7 | PMT Front-end Electronics Technical Design and Safety Revie | 2016-06-21 08:00
40SBN/2.4.2.19 | PMT Readout Electronics Technical Design and Safety Reviews | 2017-08-18 08:00
40SBN/2.4.3.3 | PMT Detector Installation Readiness Review | 2016-11-28 08:00
Laser Calibration and Cosmic Ray Tagger
40SBN/2.5.2.2.13 | CRT Design and Production Readiness Review | 2016-03-01 08:00 | 2016-03-14
40SBN/2.5.2.5.9 | Fermi lab Safety Review of CRT and Laser | 2016-06-09 17:00
40SBN/2.5.1.1.10 | Laser System Design and Production Readiness Review | 2016-03-01 08:00 | April 2017 | After cryostat design feed-back from GTT
40SBN/2.5.1.3.11 | Engineering Review of Laser System Operation | 2016-06-13 08:00
40SBN/2.5.1.4.5 | Fermi lab Safety Review of Laser Calibration System | 2016-10-12 08:00
TPC Electronics
40SBN/2.6.1.1.5 | FE ASIC and ADC ASIC Design Review for 1st Prototype Submission | 2016-02-08 | 2016-01-21
40SBN/2.6.1.1.5 | 2nd ADC ASIC Design Review for 1st Prototype Submission | 2016-02-08 | 2016-04-07 | ADC submission 6/27/2016
40SBN/2.6.3.1.1 | Signal Feed-Through and Cold Cable Design Choice | 2016-04-29 08:00 | March, 2017 | Going back to single-flange design, will eview together with WIB and NevisAfter evaluation of seal option with Technetics O-flex, can take place in one of installation meetings. 4/7 Design changed
40SBN/2.6.1.1.30 | Cold Electronics FEM Board Design Review | 2016-06-15 08:00 | March, 2017 | After prototype vertial FEMB and integration test with Nevis electronics
40SBN/2.6.3.1.16 | Feed-Through & Warm Interface Electronics Design Review | 2016-09-01 08:00 | March, 2017 | Joint Review -- agreed with Chen to do this in April 15's phone conversation
40SBN/2.6.4.1.14 | Nevis Readout Engineering Design Reviews | 2016-09-01 17:00 | March, 2017
40SBN/2.6.1.2.5 | FE ASIC and ADC ASIC Design Ready for 2nd Prototype Submission | 2016-10-24 17:00 | March, 2017 | After evaluation of new submission of FE ASIC. Review of ADC ASIC submission is expected to take place in May 2016
40SBN/2.6.1.2.26 | Cold Electronics Production Readiness and Safety Review | 2017-03-21 08:00 | Summer,2017
40SBN/2.6.1.2.5 | (T4) - [Complete] - FE ASIC and ADC ASIC Design Ready for 2nd Prototype Submission (SBN-ND-TPCE)(CE)(PD) | 2016-11-07 17:00
40SBN/2.6.1.2.30 | (T4) - [Complete] - Cold Electronics Production Readiness and Safety Review (SBN-ND-TPCE)(CE)(FD) | 2017-04-14 17:00
40SBN/2.6.1.3.17 | (T4) - [Complete] - Cold Electronics pORC Review (SBN-ND-TPCE)(CE)(P) | 2017-09-06 17:00
40SBN/2.6.3.2.15 | (T4) - [Complete] - Feed-Through & Warm Interface Electronics Production Readiness and Safety Review (SBN-ND-TPCE)(CC)(FD) | 2017-05-16 17:00
40SBN/2.6.3.3.13 | (T4) - [Complete] - Feed-through & Warm Interface Electronics pORC Review (SBN-ND-TPCE)(CC)(P) | 2017-10-17 17:00
40SBN/2.6.4.2.9 | (T4) - [Complete] - TPC Nevis readout production readiness review (SBN-ND-TPCE)(NR)(FD) | 2017-02-21 17:00
DAQ and Readout
40SBN/2.7.1.17 | Preliminary Readout and DAQ Design Review (FNAL - Labor) (SBN-ND-DAQ)(RI) | 2016-08-16 08:00 | Feb,2017 | After White Rabbit demonstration at PNNL, expect to be late summer
40SBN/2.7.2.9 | Technical Design and Safety Reviews of Readout Racks and Cabling (FNAL - Labor) (SBN-ND-DAQ)(RS) | 2017-03-30 08:00
40SBN/2.7.3.7 | Rack installation Safety Review -pORC (FNAL - Labor) (SBN-ND-DAQ)(RR) | 2018-01-30 08:00
40SBN/2.7.3.8 | (T5) - [Complete] - Relay rack is ready for installation (SBN-ND-DAQ)(RS) | 2018-04-19 17:00
40SBN/2.7.4.12 | SBND Trigger Design Review (FNAL - Labor) (SBN-ND-DAQ)(TE) | 2017-09-06 08:00
40SBN/2.7.4.17 | Trigger Hardware Operation Readiness Clearance Review (FNAL - Labor) (SBN-ND-DAQ)(TE) | 2018-03-30 08:00
40SBN/2.7.5.1.10 | Review and Agree on Detector Control Specification (FNAL - Labor) (SBN-ND-DAQ)(CS) | 2016-09-26 08:00
40SBN/2.7.5.3.6 | Detector Control System Design Review (FNAL - Labor) (SBN-ND-DAQ)(CS) | 2017-03-22 08:00
40SBN/2.7.5.5.10 | Detector control System Performance Review (FNAL - Labor) (SBN-ND-DAQ)(CS) | 2018-05-30 08:00
40SBN/2.7.6.6.9 | DAQ Test stand Operation Readiness Review (FNAL - Labor) (SBN-ND-DAQ)(TS) | 2016-09-30 08:00
40SBN/2.7.6.13 | Test stand Integration Performance Review (FNAL - Labor) (SBN-ND-DAQ)(TS) | 2018-08-02 08:00
40SBN/2.7.9.9 | pORC Review - Readout and DAQ Racks (FNAL - Labor) (SBN-ND-DAQ)(EI) | 2018-10-10 08:00
40SBN/2.7.9.13 | ORC Review - Readout Electronics (FNAL - Labor) (SBN-ND-DAQ)(EI) | 2019-07-23 08:00
40SBN/2.7.9.17 | DAQ Commissioning Test Review (FNAL - Labor) (SBN-ND-DAQ)(EI) | 2020-04-09 08:00
40SBN/2.7.9.18 | (T4) - [Ready] - DAQ is Ready for SBND Cold Runs (SBN-ND-DAQ)(EI) | 2020-04-22 17:00
Installation Coordination
40SBN/2.8.1.17 | Design Review of ND Assembly and Installation | 2016-07-28 08:00
40SBN/2.8.2.10 | Safety Review of Assembly Facility | 2016-11-29 08:00
SBND Cryostat
40SBN/2.9.1.18 | Preliminary Design Review | 2016-02-29 17:00 | June
40SBN/2.9.2.13 | Review of membrane Cryostat Design by GTT and Cryostat Top Design | 2016-05-12 17:00
40SBN/2.9.2.15 | Review for Final Design (SBN-ND-C)(FD) | 2016-05-26 17:00