## SBND_Active_Risk_By Level 2
SBND Risk List
WBS | Risk Rank | Owner | Risk Summary | Risk Impact | Mitigation Method Proposed | Resolved | Resolved By
2.1 - Program Management | High | Ting Miao | Loss of management personnel | This could delay the schedule as new management takes time to be effective | Working closely with neutrino division leadership to coordinate personnel assignment
2.3.3 APA frame | high | Kostas Mavrokoridis | APA frame flatness does not meet specification | Wire will not in desired position and this will cause potential operation issue | Design wire geometry board shimming scheme to flat out wire planes
2.3.3 APA frame | high | Kostas Mavrokoridis | Misalignment of precision holes on the wrapped side | Wire plane gaps between U/V/Y layer will be out tolerance causing performance and operation problems | Design method to reset the spacing 1)Change height of the wire-guide teeth on the U/V geomery boards for the wrapped edge; 2)Add additional wire-support combs on the wrapped edge to set wire plane spacing; 3)Other on-fly adjustment
2.3.3 APA damage during cold test | Medium | Kostas Mavrokoridis | Wire and geometry board damage during fast thermal cycling | Wire will not in desired position and this will cause potential operation issue | Design wire geometry board shimming scheme to flat out wire planes
2.3.8 HV & Feed-through | Medium | Kostas Mavrokoridis | Feed-through can not hold high voltage | Lowered operation drift field | Cold test together with protoDUNE; use same fabrication vendor as protoDUNE
2.3.7 CPA | Medium | Kostas Mavrokoridis | CPA failed to hold designed high voltage | Lowered operation drift field | Explore cold test of small CPA section with feed-through
2.4 PMT TPB coating | Low | Richard Van De Water | PMT tube TPB coating failure I | loss light detector efficiency | In-house long term test in cold
2.5.2 CRT | Low | Igor Kreslo | Increased CRT module fabrication failure rate | Delay of module fabrication schedule | 10% spare in scintillator supply
2.5.2 CRT | Low | Igor Kreslo | Module fabrication schedule delay | Delay of detector completion | Planning for training on physicist labors from collaboration universities
2.6.1 Cold Electronics | High | Hucheng Chen | Both dual-ADC option and LTC ADC not meeting design requirement | Loss resolution and dynamic range of energy measurement | Warm ADC aka uBooNE design
2.6.1 Cold Electronics | High | Hucheng Chen | Lack of engineering resource for cold electronics ASIC and system designs | Schedule delay | Work with BNL and FNAL management to secure engineering support for SBND
2.6.2 TPC warm interface | High | Hucheng Chen | Design change to increase channels and powers required by cold ADC changes | Increase cost | Delay final design and prototyping until cold electronics option be finalized
2.6.2 TPC feed-through and cable | High | Hucheng Chen | Design change to increase channels and powers required by cold ADC changes | Increase cost | Delay final design and prototyping until cold electronics option be finalized
2.7 Readout and DAQ | High | Georgia Karagiorgi and Eric Church | Cold electronics delivery or testing delays | DAQ not ready for commissioning | Exercise full DAQ system in fake data mode using planned readout functionality
2.8 Installation Coordination | Medium | Andy Stefanik | Additional design tasks due to NSF/STFC funding runout | Delay TPC assembly and installation design | Neutrino division hires additional ME for SBN
2.8 Installation Coordination | Medium | Andy Stefanik | Not enough support for QA/QC effort | Delay detector commissioning | Recruited university contribution
2.8 Installation Coordination | Medium | Andy Stefanik | Change of cold electronics design requires more singal channels going through TPC ports | TPC ports too crowed which will cause heat loss or LAr purity issue | Use spare ports and potential also ports reserved for PDS R&D for TPC readout
2.9 Cryostat | High | Min Jeong Kim | Delay of cryostat design choice | Delay TPC and CRT installation design | Working closely with CERN group